## Slide 1: Project Update: Team 2 / The Concorde
Sponsor: Mark Tschiegg
Project Manager: Alex Xia
Data as of: 03/31/2016
We spent the past week doing research work on the Concorde case.
We also started working on designing the analysis structure. We plan to meet after the Thursday class to finalize our structure.
We are in the process of updating our Gantt Chart because we lost a team member and we had to reassign all of his tasks to other team members.
Project Status
Identified key research topics and resources
Collected a good amount of useful data about the Concorde case
Key Achievements this period
Key Performance Indicators |  |  | 
Indicator | R | C | O
Overall | A | A | 
Scope | G | G | 
Budget | N/A | N/A | 
Schedule | A | A | 
Risks | A | A | 
Dependencies | A | G | 
Other |  |  | 
Other |  |  | 
Top Risks and Issues |  |  |  | 
R/I | Risk | P | I | Response Action
I | Team is shorthanded because one member dropped the class | L | H | We will re-evaluate our work and reassign some of the tasks
I | Team didn’t have weekly meeting this week due to time conflicts among team members | M | M | We had active discussions via email and completed this week’s tasks
R | Availability of team members, such as time conflict, considering this is towards the end of the semester and everyone is getting busier and busier. | M | M | Team members must make sure to notify their availability to others in the team, so that the rest of the team could plan the project tasks accordingly.
R | Additional work for the remaining team members might slow down the originally committed timeline | L | M | Team members should balance the work load amongst all and seek help from each other or Mark if needed.
Finalize the analysis structure
Finish data analysis work including analysing data, organizing and summarizing analysis
Planned for next period
What do you normally suggest teams do when they lose team members during the middle of the project?
Questions for Sponsor