## Slide 1: Project Update: Team 2 / The Concorde
Sponsor: Mark Tschiegg
Project Manager: Alex Xia
Data as of: 04/13/2016
We completed the analysis of the systematic biases that led to the failure of the Concorde project.
We have summarized the findings of the systematic bias.
We have identified the recommendations to be provided to the class as well as to the companies.
We have created a draft version of the final presentation and we are in the progress of revising it.
Project Status
Completed the analysis of the systematic bias
Created a summary of our findings
Provided recommendations
Created a draft version of the final presentation
Key Achievements this period
Key Performance Indicators |  |  | 
Indicator | R | C | O
Overall | A | A | 
Scope | G | G | 
Budget | N/A | N/A | 
Schedule | G | G | 
Risks | A | A | 
Dependencies | G | G | 
Resource | A | G | 
Other |  |  | 
Top Risks and Issues |  |  |  | 
R/I | Risk | P | I | Response Action
I | A couple of the team members got sick, which affected team’s productivity | H | M | The members who are sick immediately informed the team and asked for help to cover some of the work assigned to them.
R | Availability of team members, such as time conflict, considering this is towards the end of the semester and everyone is preparing for exams and final presentations for all courses. | H | M | Risk is mitigated by ensuring that the team members notify their availability to others in the team, so that the rest of the team could plan the project tasks accordingly.
R | The complexity of the project demands greater explanation time during the final presentation and Team is at risk of exceeding the 15 min timelines of the presentation. | M | H | Team should minimize this risk by being concise during the presentation. Reduce the probability of it happening by practicing and rehearsing the presentation as many times as possible.
Complete the final project presentation with reference to the rubric provided by the instructor.
Rehearse the presentation
Planned for next period
In the syllabus, you mentioned that our presentation should include a statement of the problem, analysis and discussion, and a conclusion in addition to answering the case questions. What do you mean by “the case questions”? Do you mean the questions from the class during our presentation or there’s a list of questions somewhere we need to answer?
Is the problem statement same for the charter and the presentation ?Should it identify the systematic biases or should it be to educate the class on how systematic biases can lead to the failure while managing projects.
Questions for Sponsor